Project Status Report for Virtual Server Implementation

Project Name: 		Virtual Server Implementation

Project Manager: 	Randy Keefer

Team Members: 	Tammi Cascone, Randy Keefer, Jeffrey Redington, Steven Pawlus

Report Date: 		June 22, 2008

Reporting Period: 	May 7, 2008 to June 22, 2008

# Table of Contents

Management Summary 1

Key Milestones Table 2

Schedule 2

Effort 4

Cost 4

Requirements Status 5

Communications summary 5

Top Five Risks 6

Open Issues 7

Action Items 7

Lessons Learned 7

Appendices 7

# Management Summary

The virtualization project team has spent the majority of time thus far documenting and identifying server infrastructure components, performing capacity analysis and evaluating technology options for virtualization, backup/recovery, SAN storage, and server platforms. The team is currently running one week behind plan, primarily due to unforeseen difficulties in obtaining information on the current infrastructure as well as obtaining technology vendor input. The team expects to quickly make up lost time, as the documentation obtained concerning required capacity and application platforms appear to be favorable for virtualization. It is anticipated that few changes will be necessary to the infrastructure to accommodate server virtualization. . It also appears that the virtualization software decision will be an easy one, given the flexibility, tenure, and robust feature set of VMWare over Microsoft Hyper-V. It is expected that the technology decision and detailed design will begin on 6/23/08, and will quickly make up lost time and continue as per the original schedule.

| Defined milestones completed: | 6 of 6 (100%) |
| --- | --- |
| Defined tasks completed: | 6 of 6 (100%) |
| Total estimated project hours used: | 800 of 1,440 (56%) ** Does not include contingency |
| Ahead of (or Behind) schedule by: | 7 Days behind Schedule |
| Known defects: | None Found |
| Contingency hours remaining: | 100% of 10 Days (320 Hours) |

# Key Milestones Table

| ID | Title | Planned Completion Date | Previous Forecast Completion Date | Current Forecast Completion Date | Actual Completion Date |
| --- | --- | --- | --- | --- | --- |
| 1 | Infrastructure Analysis | 6/7/2008 | 6/7/2008 | 6/20/2008 | 6/20/2008 |
| 2 | Industry Analysis | 6/14/2008 | 6/14/2008 | 6/20/2008 | 6/20/2008 |
| 3 | Status Report #1 | 6/15/2008 | 6/15/2008 | 6/22/2008 | 6/22/2008 |

# Schedule

| Current Week | 05/18 to 05/24 | 05/25 to 05/31 | 06/01 to 06/07 | 06/08 to 06/14 | 06/15 to 06/21 | 06/22 to 06/28 | 06/29 to 07/05 | 07/06 to 07/12 | 07/13 to 07/19 | 07/20 to 07/26 | 07/27 to 08/02 | 8/03 to 8/09 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 - Development Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Hardware Assessment |  |  |  |  |  |  |  |  |  |  |  |  |
| Software Configuration |  |  |  |  |  |  |  |  |  |  |  |  |
| Capacity & Performance Analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Industry Analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Virtualization Alternatives |  |  |  |  |  |  |  |  |  |  |  |  |
| SAN Storage Alternatives |  |  |  |  |  |  |  |  |  |  |  |  |
| Backup Alternatives |  |  |  |  |  |  |  |  |  |  |  |  |
| Virtual Infrastructure Design |  |  |  |  |  |  |  |  |  |  |  |  |
| Design Presentation |  |  |  |  |  |  |  |  |  |  |  |  |
| Server Implementation - TBD |  |  |  |  |  |  |  |  |  |  |  |  |
| Tasks Weeks | 05/18 to 05/24 | 05/25 to 05/31 | 06/01 to 06/07 | 06/08 to 06/14 | 06/15 to 06/21 | 06/22 to 06/28 | 06/29 to 07/05 | 07/06 to 07/12 | 07/13 to 07/19 | 07/20 to 07/26 | 07/27 to 08/02 | 8/03 to 8/09 |

| Initial estimated completion date: | 7/20/2008 |
| --- | --- |
| Previous estimated completion date: | 7/20/2008 |
| Current estimated completion date: | 7/20/2008 ** (Does not include contingency) |

# Effort

The total actual expended hours for the project to date is 800 hours (40 hours/FTE * 5 weeks). The total planned project hours are 1440, not including a contingency of 320 hours. Planned hours through the completion of the Infrastructure Analysis and Industry Analysis tasks was 640 hours, but due to the additional effort required slightly overran the plan.

| Life Cycle Activity | This Reporting Period (labor-hours) |  | Project to Date (labor-hours) |  |
| --- | --- | --- | --- | --- |
|  | Planned Effort | Actual Effort | Planned Effort | Actual Effort |
| Hardware Assessment | 100 Hours | 140 Hours | 100 Hours | 140 Hours |
| Software Configuration | 100 Hours | 140 Hours | 100 Hours | 140 Hours |
| Capacity & Performance Analysis | 40 Hours | 120 Hours | 40 Hours | 120 Hours |
| Virtualization Alternatives | 100 Hours | 180 Hours | 100 Hours | 180 Hours |
| SAN Storage Alternatives | 100 Hours | 180 Hours | 100 Hours | 180 Hours |
| Backup Alternatives | 40 Hours | 40 Hours | 40 Hours | 40 Hours |

# Cost

| Life Cycle Activity | This Reporting Period |  | Project to Date |  |
| --- | --- | --- | --- | --- |
|  | Planned Cost | Actual Cost | Planned Cost | Actual Cost |
| Hardware Assessment | $3000 | $4200 | $3000 | $4200 |
| Software Configuration | $3000 | $4200 | $3000 | $4200 |
| Capacity & Performance Analysis | $1200 | $3600 | $1200 | $3600 |
| Virtualization Alternatives | $3000 | $5400 | $3000 | $5400 |
| SAN Storage Alternatives | $3000 | $5400 | $3000 | $5400 |
| Backup Alternatives | $1200 | $1200 | $1200 | $1200 |

# Requirements Status

- Document current Infrastructure, Applications and Capacity requirements - Completed.

- Document Industry Virtualization, SAN, and Backup/Recovery alternatives – Completed.

# Communications summary

| Communications |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Date | How | Issue | Outcome |
| Team Meeting | May 7, 2008 | Franklin Live | Project Ideas | Meet next night to vote on project |
| Team Meeting | May 8, 2008 | Franklin Live | Voted on project | Virtual server |
| Professor Smith | May 9, 2008 | Email | Tips on project of this type | Lots of diagrams and visuals-before and after and where resources are delivered |
| Team Meeting | May 11, 2008 | Franklin Live | Divide up responsibilities for team members | Team members accepted their responsibilities |
| Team Collaboration | May 20, 2008 | Doc sharing program | Add and edit vision and scope doc | Uploaded doc to Google docs and sent invitations |
| Team Meeting | May 24, 2008 | Franklin Live | Finalize vision and scope doc | Finalized draft and email to team leader for final review |
| Team Meeting | May 27, 2008 | Franklin Live | Keeping on schedule | Review Status |
| Professor Smith | May 29, 2008 | Email | Feedback on vision and scope doc | Revised V &S doc to reflect feedback |
| Business Practitioner | May 30, 2008 | Email | Feedback on V & S doc | Revised V&S doc to reflect feedback |
| Team Meeting | June 3, 2008 | Franklin Live | Keeping on schedule | Review Status |
| Team Collaboration | June 3, 2008 | Doc sharing program | Add and edit Status Review Doc | Uploaded doc to Google doc and sent invitations |
| Team Meeting | June 10, 2008 | Franklin Live | Keeping on schedule | Review Progress; Determine next steps for Deliverables |
| Team Meeting | June 17, 2008 | Franklin Live | Keeping on schedule | Re Review Progress; Obtain current status for Status Report #1. |
| Team Meeting | June 22, 2008 | Franklin Live | To Finalize Status Report | Finalized Status Report |

# Top Five Risks

- Server room environmentals (Power Requirements, Rack Space, Cooling, UPS capacity).

- Device malfunctions

- Completing the project over budget

- Completing the project outside of deadline

- Project team member (s) unavailable

# Open Issues

No budget has been originally set for the virtualization project as part of the Vision and Scope. The planned replacement cost for the server infrastructure is assumed to be the maximum budget amount. This needs to be confirmed with the project sponsor.

# Action Items

Completed Items:

Completed Infrastructure Analysis and Industry Analysis.

New Items:

Confirm Virtualization Project Budget.

# Lessons Learned

- Contingency was added to the back of the project instead of at each task level. Spreading contingency time out would help to manage the task timeline and require fewer adjustments.

- Timeline needs to take into account project team member unavailability

# Appendices

Documents in the Project Artifacts folder include:

Original Vision and Scope -

ITEC495-V1WW-Team3-1.3.2.doc;

Feedback document from Professor Smith –

ITEC495-V1WW-1-3-2-Keefer-Randall-1-2008-05-29-1.doc;

Feed Back document from Mike Midkiff with team comments –

Midkiff_Review V&S_Team3 Comments.doc;

Revised Vision and Scope –

ITEC495_V1WW-Team3-1.3.2_v4.doc;

Rack diagrams of Production Servers –

Production_Server_Rack_Diagram-Revision2.vsd;

Rack diagrams of Test Servers –

Test_Server_Rack_Diagram-Revision2.vsd;

Rack diagrams of Development Servers –

Development_Server_Rack_Diagram-Revision2.vsd;

Infrastructure Analysis (Server List and Capacity analysis) –

SMEBCO-Server-List-Revision3.xls;

Infrastructure Analysis Write-up –

Infrastructure_Analysis_Summary.doc;

Market Survey (Alternatives Analysis) –

Market_Survey.xls;

Market Survey Write-up –

Market_Survey_Summary.doc;

Project Plan (Microsoft Project 2007 format) –

Virtual Solutions - SMEBCO Project Plan.mpp;