Status Report I

Transportable Voice, Data, and

Wireless Communications System

Developed for the

American Red Cross of

Greater Columbus

Version 1.0

Prepared by

*

Jamison Ables

Paulo Cambraia

Michael Clark

FAbrione Donyeau

June 20, 2008

* Franklin University-ITEC495-V1WW-S08-Team4

1.	Management Summary	3

2.	Key Milestones Table	4

3.	Schedule	4

4.	Effort	5

5.	Cost	6

6.	Requirements Status	7

7.	Communications Summary	8

8.	Top Five Risks	8

9.	Open Issues	9

10.	Action Items	10

11.	Lessons Learned	11

12.	Appendices	12

# Management Summary

Part of the success of the project is dependent on the cooperation and proper functioning of the team. Quattro Consulting has been successfully meeting deadlines with a high-degree of quality since project inception. When scheduling conflicts could impact the completion of important tasks, other team members have taken different roles in the group to assure task completion.

The bulk of the research and documentation required for this project will happen over in the period between the two required project status reports. While general assignments for these tasks have been agreed upon, specific scheduling of due dates is still pending. The client is particularly interested in the projected costs as they relate to their requested features. Quattro Consulting intends to create two or three high-level cost estimates prior to the next project status deliverable in order to provide the opportunity for the client to consider the scope and how the costs might be documented in the report. This is particularly important as the ARCGC must justify and obtain funding for the project components to determine feasibility.

| Defined milestones completed: | 2 of 5 (40%) |
| --- | --- |
| Defined tasks completed: | 3 of 11 (27.3%) |
| Total estimated budget used: | $4,785 of $22,000 (21.75%) |
| Ahead or behind schedule by: | On schedule |
| Budget remaining: | $17,215 |

# Key Milestones Table

| ID (Gantt) | Title | Planned Completion Date | Previous Forecast Completion Date | Current Forecast Completion Date | Actual Completion Date |
| --- | --- | --- | --- | --- | --- |
| 2 | Gather User Requirements | 5/11/2008 | 5/11/2008 | 5/11/2008 | 5/11/2008 |
| 3 | Write Vision and Scope Document | 5/18/2008 | 5/18/2008 | 5/18/2008 | 5/18/2008 |
| 5 | Status Report I | 6/15/2008 | 6/14/2008 | 6/14/2008 |  |
| 10 | Status Report II | 7/6/2008 |  |  |  |
| 15 | Final Document | 8/7/2008 |  |  |  |

# Schedule

| Initial estimated completion date: | 8/7/2008 |
| --- | --- |
| Previous estimated completion date: | 8/7/2008 |
| Current estimated completion date: | 8/7/2008 |

# Effort

| PV = Planned Value (manhours) |  |  |  |
| --- | --- | --- | --- |
| EV = Earned Value = % Completed * Total PV at Completion |  |  |  |

To date, the project has been executed and kept on schedule, without any major discrepancies. There is a slight shift in manhours, probably due to extra effort put into the project initially.

# Cost

| PV = Planned Value (dollars) |  |  |  |
| --- | --- | --- | --- |
| EV = Earned Value = % Completed * BAC (Budget at Completion) |  |  |  |

No major discrepancies have occurred as far as budgeting goes. Normal deviations from the PV line are expected and attributed to random factors.

# Requirements Status

Through an immersive analysis, the members of Quattro Consulting, LLC have developed a well defined list of business and user requirements.  Such activities are outlined in the following table with an accommodating legend which identifies the status of each requirement to date:

C-Complete,  A-Approved,  I-Implemented, Verified,  R-Rejected,  D-Deleted

| Requirement | Status | % |
| --- | --- | --- |
| Identify and Develop Team Project | C | 100% |
| Identify Business Project Proposal | C, A | 100% |
| Identify Business Practitioner (BP) | C, A | 100% |
| Business Proposal Acceptance | C, A | 100% |
| Team Member Assigned Responsibilities | C, A, I | 100% |
| Project Vision and Scope Establishment | C, A, I | 100% |
| Budget and Cost Analysis | C, A, I | 25% |
| Project Schedule Established | C, A, I | 100% |
| Project Vision and Scope Implementation | C, I | 100% |

# Communications Summary

# Feedback from the instructor was mostly positive.  The area requiring the most clarification was regarding project risks.  The Vision and Scope document (in the archive) has been amended to include the Top-5 Risk and Mitigation table from this project status report.  The summary of actions has been completed according to the ITEC 495 Project Feedback Form.  In addition to the changes described below, a variety of minor formatting, spelling, and grammatical changes were made. Overall, much of the feedback was positive, and the lead reviewer (Professor Wayne Smith) recommended no substantive corrections.  The Business Practitioner (Kevin Liston) has been very helpful to the team in communicating the requirements and possible options.  Contact with the organization and accomplishments to date include:

# Three individual meetings with the ARCGC Business Practitioner by the Project Lead. Information shared with project team during weekly team meeting.

# Audio conference call with Kevin Liston and the entire Project Team prior to completion of the Vision and Scope document.

# Site visit to ARCGC headquarters by the Project Lead.  This included meeting with the Business Practitioner’s supervisor, James Sage, and photographic session of the communications vehicle for the proposal.  Information garnered about the session was shared with the project team during weekly team meeting.

# All noted risks have been targeted and isolated resulting in a severity level being assigned to each such risk. For the specification of each known risk and assigned severity, please reference Section 8 of this document titled “Top Five Risks”, including supporting Table.

# Subsequent documents will indicate potential ‘process’ risks that are directly associated with collaboration and/or communication. Currently, there are no issues that would have a substantial impact pertaining to the communication channels by the team members of Quattro Consulting, LLC solution.

# Subsequent documents will depict a visual representation of the Quattro Consulting, LLC solution. The improvement and upgrade factors will be the primary focus as the illustrations will contrast each server prior to, and after Communication Systems upgrades.

# Top Five Risks

| Risk | Severity | Mitigation |
| --- | --- | --- |
| Funding for a new communications system may not be available. | HIGH | By presenting older and newer technology platform options, older, less-expensive equipment may be able to be substituted, either by purchase or donation. |
| Cellular data coverage may not be available at every site | HIGH | Platform will be capable of other connectivity options, such as T1 or wireless LAN. Local wireless IP telephony feature will function without cellular data coverage. |
| Wireless LAN system may experience interference | Medium | System designed for multi-frequency and multi-band operation, and configured for auto frequency assignment, reducing the chance of frequency congestion. |
| Operators may not fully understand how to configure system features | Medium | Pre-configured features will be enabled and documented. The process to reload the feature set from a computer file will be included. |
| Cellular carriers may not share detailed coverage maps for the complete area | Medium | General maps can be interpolated. The cellular tower database may be used (for a fee). |

# Open Issues

A current open issue is the hardware that we will utilize hasn’t been determined. Instead of choosing the hardware right now we will develop two or three different options to give the customer better opportunity for success. We have chosen to utilize Cisco products for the majority of our solution, which will help keep the choices constant. In the next two weeks we will have a detailed breakdown for each option.

# Action Items

The following activities have been acknowledged and upon implementation, each item will be documented as such according to the activity priority.

- Gathered requirements.

- Wrote Vision and Scope document.

- Selected business practitioner.

- Received and analyzed feedbacks from business practitioner and instructor.

- Status report 1 is in progress.

- Network diagram is in progress.

- Coverage area map is in progress.

- Select network provider: to be completed.

- Write status report 2: to be completed.

- Spec hardware and software: to be completed.

- Estimate cost for selected hardware/software: to be completed.

- Installation and configuration: to be completed.

- Write final document: to be completed.

- Training: to be completed.

# Lessons Learned

The Quattro Consulting, LLC ‘Team Initiative’ provided experts in both technical and management practices for the development of a large-scaled communications system.  The following comments summarize the lessons learned and will prove beneficial for further operations, strategic planning and the implementation of best practices.

- Simple and clear communication has resulted in a solid foundation and successful business relationship among the members of Quattro Consulting, LLC.  We strategically engaged our objectives and obtained feedback pertaining to our processes.  These processes were then used to identify each member’s ability to contribute skills that were both qualitative and quantitative

- We have collectively managed the flow of the project, while demonstrating to our customer the added benefits of our services while offering a suite of alternatives that will enable the customer to optimize these services.

- Business Practitioner, Kevin Liston has clearly indicated that not only is the project idealistic, but realistic in terms of developing a Communications System that answers to the immediate and specified needs of the Red Cross Columbus Chapter, without question.

- The use of the audio conferencing bridge, coupled with email, has been a very effective communications tool for Quattro Consulting, as it has allowed the ability to better share ideas in a conversational manner that is not available with Franklin Live or chat tools.

- Having the whole team able to meet the Business Practitioner in an audio conferencing session was also very effective.  Instead of a single member attempting to translate the business requirements and focus, team members were able to interactively address their concerns and gain clarification from the practitioner.

- Given the project goal of creating a communications system for a specific-type of vehicle, the ability to provide photographs of the vehicle and the environment were helpful in explaining various design parameters.

# Appendices

# The following documents can be found in the “artifacts” folder, which is compiled 	together with the Status Report 1 in the ZIP archive provided:

- Revised Vision and Scope document
Original Vision and Scope document with updated information such as updated Gantt chart and changes proposed in the feedback document.

- Feedback from instructor
Feedback on the version 1 of our Vision and Scope document provided by Professor Wayne.

- Gantt chart
Updated chart to reflect new and updated tasks and milestones.

- Earned Value Management spreadsheet
Spreadsheet with calculation and charts to show our progress in manhours and dollars.

- Coverage maps
Coverage areas for the two main network providers, Verizon and Sprint. Maps are for Central Ohio area only.