A-Team Networking

Providing a team approach to network design

Project Status Report #1

Network Upgrade Project

for

The ABC Law Firm

Prepared by

Project Lead: David Dalton

Abdalla Al Ansari

Charles Legg

Eric Wright

A-Team Networking

Report Date: February 22, 2009

Reporting Period: January 12 to February 21, 2009

# Table of Contents

Table of Contents	i

Management Summary	2

Key Milestone Table and Project Schedule	3

Effort	4

Cost	5

Requirements Status	6

Communications summary	7

Top Five Risks	9

Open Issues	10

Action Items	10

Lessons Learned	11

Appendices	16

# Management Summary

The ABC Law Firm network grade project is on track and meeting the schedule as presented in the original vision and scope document.  Over the past few weeks, A-Team Networking has accomplished the following milestones:

- Initial version of the Vision and Scope Document

- Initial site survey and documentation of the ABC Law Firm

- Installation of the fiber optic cabling between buildings

- Completion of all power upgrades by Arrow Electric

- Procurement of Cisco Hardware

- Installation of the Cisco switches in Buildings A and B

- Delivery of the first project report to the client

The accomplishment of all milestones took place within the schedule dates shown in Table 1, with the exception of item number 3, electrical upgrades.  This delay was due to a parts procurement problem involving an electrical vendor of Arrow Electric.  This delay is outside the scope of A-Team Networking as Arrow Electric is a subcontractor of the law firm.  Even so, the completion of the power upgrade was within acceptable limits of the project and caused no major delays.

A summary of the project statistics follows:

- Defined milestones completed 6 of 15 (40%)

- Defined total tasks completed 120 of 139 (86%)

- Estimated total project hours used 981 of 1760 (56%)

- Estimated total budget spent $414,080 of $800,000 (52%)

- On schedule by 0 labor-hours, 0 days

- Known defects found are 0 with 0 found

- The are 100% of 264 contingency hours remaining

# Key Milestone Table and Project Schedule

There are 15 key milestones for this project.  Table 1 lists these milestones and their associated completion dates while Table 2 provides a Gantt Chart of the same milestones.

| Table 1: Project milestones |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ID | Title | Planned Completion Date | Previous Forecast Completion Date | Current Forecast Completion Date | Actual Completion Date |
| 1 | Site Survey | 1/23/09 | 1/23/09 | 1/23/09 | 1/22/09 |
| 2 | Procurement of Hardware & Equipment | 2/10/09 | 2/10/09 | 2/10/09 | 2/08/09 |
| 3 | Installation of New Fiber Cable | 2/06/09 | 2/06/09 | 2/06/09 | 2/06/09 |
| 4 | Power Upgrades (Arrow Electric) | 2/06/09 | 2/06/09 | 2/23/09 | - |
| 5 | Pre-stage Configuration | 2/19/09 | 2/19/09 | 2/19/09 | 2/19/09 |
| 6 | Build & Initial Configuration | 2/19/09 | 2/19/09 | 2/19/09 | 2/19/09 |
| 7 | Hardware Installation | 3/12/09 | 3/12/09 | 3/12/09 | - |
| 8 | Delivery of Project Report #1 | 2/22/09 | 2/22/09 | 3/01/09 | 3/01/09 |
| 9 | Testing | 3/13/09 | 3/13/09 | 3/13/09 | - |
| 10 | Delivery of Project Report #2 | 3/15/09 | 3/15/09 | 3/15/09 | - |
| 11 | Production Conversion Weekend | 4/12/09 | 4/12/09 | 4/12/09 | - |
| 12 | First Production Day Post Conversion | 4/13/09 | 4/13/09 | 4/13/09 | - |
| 13 | Delivery of Final Project Report | 4/12/09 | 4/15/09 | 4/15/09 | - |
| 14 | Removal & Disposal of Old Equipment | 4/17/09 | 4/17/09 | 4/17/09 | - |
| 15 | Delivery of Project Presentation | 4/18/09 | 4/18/09 | 4/18/09 | - |

Table 2: Gantt Chart of Project Milestones

# Effort

The estimated total labor hours of the project are 1472 hours as shown in Table 3.  The calculation of total labor costs shown in Table 4 are from Table 3 figures.

| Table 3: Time associated with life cycle activity of the project |  |  |  |  |
| --- | --- | --- | --- | --- |
| Life Cycle Activity | This Reporting Period |  | Project to Date |  |
|  | (labor-hours) |  | (labor-hours) |  |
|  | Planned Effort | Actual Effort | Planned Effort | Actual Effort |
| Initial Site Survey |  |  |  |  |
| Network Hardware Inventory | 64 | 63 | 64 | 63 |
| Existing Logical Configuration | 64 | 63 | 64 | 63 |
| Facilities |  |  |  |  |
| Verify power requirements | 8 | 8 | 8 | 8 |
| Verify cooling capabilities | 16 | 15 | 16 | 15 |
| Cable Plant |  |  |  |  |
| Obtain Cable Plant Blueprints | 24 | 24 | 24 | 24 |
| Verify Fiber Conduit | 24 | 24 | 24 | 24 |
| Procurement |  |  |  |  |
| Obtain Pricing | 8 | 8 | 8 | 8 |
| Order | 8 | 8 | 8 | 8 |
| Build |  |  |  |  |
| Switches |  |  |  |  |
| Datacenter | 80 | 79 | 80 | 79 |
| Building A IDF | 80 | 81 | 80 | 81 |
| Building B IDF | 80 | 79 | 80 | 79 |
| Wireless | 80 | 81 | 80 | 81 |
| Cable Plant | 8 | 8 | 8 | 8 |
| Installation of new Fiber | 224 | 220 | 224 | 220 |
| Power Upgrades | external | external | external | external |
| Pre-staging configuration |  |  |  |  |
| Build and Initial Config | 224 | 220 | 224 | 220 |
| Hardware Installation | 480 |  | 480 |  |
| Testing |  |  | 32 |  |
| Production Conversion Weekend |  |  | 96 |  |
| First Production Day Post Conversion |  |  | 32 |  |
| Delivery of Final Documentation & Project Sign Off |  |  | 64 |  |
| Removal and Disposal of old Equipment |  |  | 64 |  |
| Total Labor Hours | 1472 | 1457 | 1760 | 981 |

# Cost

The estimated total cost of the ABC Law Firm project is $800,000, which includes all labor ($300,000) and hardware ($500,000) costs.  The project has a built-in contingency overrun of 15 percent ($120,000) without executive approval of the ABC Law Firm.  Tables 4 and 5 provide a breakdown of the total cost of the project to date.  Labor costs of $125 per hour reflect the labor hours in Table 3.  The actual hardware and labor costs are very close to the projected amounts.

| Table 4: Cost associated with life cycle activity of the project, cost basis is $125 per hour |  |  |  |  |
| --- | --- | --- | --- | --- |
| Life Cycle Activity | This Reporting Period |  | Project to Date |  |
|  | Planned Cost | Actual Cost | Planned Cost | Actual Cost |
| Initial Site Survey |  |  |  |  |
| Network Hardware Inventory | $8,000 | $7,875 | $8,000 | $7,875 |
| Existing Logical Configuration | $8,000 | $7,875 | $8,000 | $7,813 |
| Facilities |  |  |  |  |
| Verify power requirements | $1,000 | $1,000 | $1,000 | $1,000 |
| Verify cooling capabilities | $2,000 | $1,875 | $2,000 | $1,875 |
| Cable Plant |  |  |  |  |
| Obtain Cable Plant Blueprints | $3,000 | $3,000 | $3,000 | $3,000 |
| Verify Fiber Conduit | $3,000 | $3,000 | $3,000 | $3,000 |
| Procurement |  |  |  |  |
| Obtain Pricing | $1,000 | $1,000 | $1,000 | $1,000 |
| Order | $1,000 | $1,000 | $1,000 | $1,000 |
| Build |  |  |  |  |
| Switches |  |  |  |  |
| Datacenter | $10,000 | $9,875 | $10,000 | $9,813 |
| Building A IDF | $10,000 | $10,125 | $10,000 | $10,125 |
| Building B IDF | $10,000 | $9,875 | $10,000 | $9,875 |
| Wireless | $10,000 | $10,125 | $10,000 | $10,125 |
| Cable Plant | $1,000 | $1,000 | $1,000 | $1,000 |
| Installation of new Fiber | $28,000 | $27,500 | $28,000 | $27,500 |
| Power Upgrades (external to project scope) | n/a | n/a | n/a | n/a |
| Pre-staging configuration |  |  |  |  |
| Build and Initial Config | $28,000 | $27,500 | $28,000 | $27,500 |
| Hardware Installation | $60,000 |  | $60,000 |  |
| Testing | $4,000 |  | $4,000 |  |
| Production Conversion Weekend | $12,000 |  | $12,000 |  |
| First Production Day Post Conversion | $4,000 |  | $4,000 |  |
| Delivery of Final Documentation & Project Sign Off | $8,000 |  | $8,000 |  |
| Removal and Disposal of old Equipment | $8,000 |  | $8,000 |  |
| Total Cost | $184,000 | $182,125 | $220,000 | $122,625 |

| Table 5: Hardware and equipment costs |  |  |  |  |
| --- | --- | --- | --- | --- |
| Component | Description | Qty | Unit Cost | Ext. Cost |
| WS-C6509-E | Catalyst 6500 9-slot chassis | 3 | $5,890 | $17,670 |
| WS-C6509-E-FAN | 6509-E Chassis Fan Tray | 3 | $310 | $930 |
| WS-CAC-6000W | 6500 6000W AC power supply | 6 | $2,960 | $17,760 |
| WS-X6K-S2-MSFC2 | 6500 Sup Engine-3, 2GE, plus MSFC-2 / PFC-2 | 6 | $13,637 | $81,822 |
| WS-X6548-GE-TX | 6500 Ethernet 10/100/1000 48-port Module | 12 | $7,800 | $93,600 |
| WS-X6704-10GE | 6500 Catalyst 4-port 10-Gigabit Ethernet Switch Mod | 3 | $11,299 | $33,897 |
| WS-G5484 | Cisco GBIC 10000BASE-SX Multimode Fiber Module | 5 | $325 | $1,625 |
| Cisco X2-10GB-LX4 | Cisco 10GBASE-LX4 X2 Module for MMF | 8 | $1,974 | $15,792 |
| CON-SNTP-WS-C6509 | 24x7x4 Service, Catalyst 6509 | 3 | $3,106 | $9,318 |
| AIR-AP1131AG-A-K9 | Cisco Aironet 1131AG | 1 | $484 | $484 |
| CON-SNT-AIRAP11A | 24x7x4 Service for Aironet 1131 | 1 | $57 | $57 |
| CAB-GELX-625 | Mode conditioning patch cable 62.5u, dual SC connect | 8 | $370 | $2,960 |
| N490-016-SCSC | Tripp Lite 1-U 16 Port Fiber Patch Panel - SC | 3 | $160 | $480 |
| FSDP606Y | 62.5/125um MM Armored Cable - 6 fiber | 200 | $9 | $1,800 |
| CN1 | Panduit Net-Access Cabinet with cable management | 3 | $4,420 | $13,260 |
| Network Hardware Total |  |  |  | $291,455 |

# Requirements Status

Initial Site Survey

A-Team Networking met with the information technology team at ABC Law Firm and successfully performed the initial site survey with no problems.

Procurement of Cisco Hardware

Once the site survey was complete on January 22, 2009, A-Team Networking compiled a list of required equipment for this project.  The procurement of the hardware and equipment has been received by A-Team Networking.

Installation of fiber optic cable between buildings

A-Team Networking pulled the new fiber optic cable between building A and B using the existing underground conduit the week of February 2nd, 2009, encountering no problems as the existing conduit is in good condition.

Power Upgrades

There has been a delay in the installation of the electrical power upgrades by Arrow Electric.  The delay is due to parts being on back order, which is delaying the completion of the upgrades to the week of February 23, 2009.

Pre-stage Configuration of hardware

A-Team Networking has completed the build and the initial configuration of all Cisco switches.  The testing of all switches is complete and was transported to the ABC Law Firm on February 19, 2009 in preparation for installation.

Installation of Switches

The installation of switching hardware is underway at the current time with an anticipated completion date of March 12, 2009.

Fulfillment of Future Requirements

A-Team Networking still needs to test all hardware once installed, migrate the entire firm over to the new network infrastructure, remove and dispose of old 3-Comm hardware, and deliver a final project document and presentation.

# Communications summary

Feedback from Professor Wayne Smith

A-Team Networking received feedback from Professor Smith on February 5, 2009 concerning the Vision and Scope document submitted on February 1, 2009.  In general, the feedback was positive with a few exceptions.  One recommendation is that section 1-3 concerning success criteria should contain criteria that are more specific and is quantifiable using measurable criteria, preferably numbers, or metrics of some type.

An additional comment concerned the major features of the Vision section 2-2.  Professor Smith had concern that some parts of the project lacked detail, such as the major features of the Wi-Fi segment and electrical power availability and backup provision.  He requested that the next version of document address these issues.

Professor Smith also felt that information was lacking within section three concerning scope and limitations.  Two items needing clarification are the size of the building, which will dictate the type of network backbone (copper or fiber), and what the IP configuration will be for the new network.

Finally, Professor Smith would like to see in section 5-1 concerning the team charter how the administration and resolutions of issue conflicts among the team members would occur.  The next version of the Scope and Vision Document will incorporate these recommendations.

Feedback from business practitioner Mr. Christopher Jackson

Mr. Christopher Jackson agreed to act as the business practitioner for Team-A.  He is an information technology account manager (ITAM) for the Department of Technology, City of Columbus and a Franklin University graduate with a Master degree in business administration.  Mr. Jackson provided feedback on February 10, 2009 concerning Team-A’s Vision and Scope document.  He was impressed with the detail of the Vision and Scope document and believed it was a good document to set the tone of the project.  He will be reviewing ongoing documentation from Team-A as we progress with the capstone project.

Exchanges with the project stakeholders and client

A-Team Networking has had two face-to-face meetings to plan and organize the project.  The first meeting was on January 17, 2009 to discuss project goals and target dates.  The second meeting was February 14, 2009.  During this meeting, discussion of the project status and the cost of hardware and labor for the project were finalized.  The IP configuration was determined as well as documentation for the project.  Numerous other discussions have taken place via email.

Team-based communications issues

The email outage Franklin University experienced the week of February 9, 2009 did cause confusion in the sharing of emails and documents between team members, especially since the team was not directly aware of this outage until it became apparent that emails were being lost without the sender’s knowledge.  Franklin University restored email services within 24 hours, but several emails were lost during the outage, resulting in team members having to resend those emails and documents.

# Top Five Risks

The top five risk exposures concerning this project are:

- Lost time from a team member’s illness or separation form the company

- Collapsed or damaged conduit connecting the two buildings

- Discovery of non-CAT 5e cabling within the existing network

- Equipment and hardware delivery delays

- Failure of electrical contractor to finish electrical upgrades

Of the five risk exposures, none have posed a concern at this time.  The conduit between buildings appears to be operational and all cabling inspected during the site survey appears to be acceptable for the network upgrade.  Upon ordering of equipment and hardware, the vendor indicated no anticipated delays.  The electrical contractor has a slight delay, but plans on beginning upgrades to electrical power circuits the week of February 23, 2009.  This will not delay the project as testing will not take place until the middle of March.

# Open Issues

The only open issue as of February 22, 2009 is the delay in the installation of the electrical power upgrades.  Arrow electric ensures A-Team Networking that the upgrades will be complete the week of February 23, 2009.

# Action Items

Completions of the following action items have taken place over this reporting cycle:

- Site survey of the ABC Law Firm is complete including meeting with the Arrow Electric electricians to verify all power requirements of the new hardware.

- Installation of the fiber cabling between buildings and between first and second floor of building A is complete.

- Equipment and hardware order placed with vendor.

- A-Team Networking took delivery at our offices of all hardware and equipment.

- Pre-stage configuration is complete.

- The delivery of all hardware and equipment to the ABC Law Firm took place on Friday, February 20, 2009.  Initiation of hardware installation is currently underway.

Completion delay of the following action item will not have an immediate impact on project:

- Arrow Electric reported a delay in the completion of electrical upgrades due to parts on back order.  The contractor assures us that all upgrades will be complete by February 27, 2009.  This will not delay the installation of equipment, as the mounting of equipment requires no additional power, and the scheduling of equipment testing is not until March 13, 2009.

The following action items will occur over the next reporting cycle:

- The completion of all electrical power upgrades by third party contractor.

- The installation of all equipment at the client’s location

- The testing of hardware configurations

- Review of remainder technology education items with the entire team.

# Lessons Learned

It was discovered that the initial Cisco Aironet AP that was recommended is so new that it is not readily available out in the market place.  As a result, we defaulted back to the most recent model, the Aironet 1131AG.

Being organized is important in any project.  Assembling all the documents required for the project requires an eye to detail and careful tracking of documents required for the project.

We have been experiencing difficulties with team members providing their deliverables by the date agreed upon.  In addition, some of the deliverables have been incomplete.  Everyone has to pay close attention to the quality and timeliness of his or her assigned deliverables.

Technology Information Gained

This project has provided the opportunity to gain valuable educational information into advanced network design concepts.  For the configuration to date, these concepts include the following:

- Deploying high availability Cisco 6509 switches

  - VLAN Configuration

Vlan configuration is accomplished by defining the Vlans and then assigning specific interfaces to their appropriate Vlan.  The exact configuration is as follows. The commands are typed from privileged / configuration mode to create vlan 20 and then assign ports 1 – 20 on blade 4 to this vlan:

Vlan 10

Interface range gige 4/1 – 20

Switchport mode access

Switchport access vlan 20

No shut

This same group of configuration commands can then be used for creating the other vlans and for assigning the appropriate ports to those vlans.  The interface range command allows the engineer to assign the same configuration to a range of ports which reduces the time it takes to enter the configuration. The exact configuration of each of the three switches is not given here as this is a very straightforward concept.  The Core switch and Access switch 1 have all the Vlans in the network configured on them.  Access switch 2 only has Vlan 3 for the workstations in Building B and Vlan10 as it participates in the management Vlan.

Trunk configuration

In order to extend Vlans across multiple switches in an organization over a single link, a trunk must be created.  A trunk connects two Ethernet ports on separate switches for the purpose of passing multiple Vlan traffic.  Both sides of the trunk must be configured the same for the trunk to successfully come up.  It is also good practice to only include Vlans in the trunk that are necessary between the two switches.  Configuring additional Vlans can add unnecessary traffic to the trunk thus degrading critical production traffic.  It should be noted that Cisco’s proprietary trunking protocol, ISL, is not supported on 10 Gigabit interfaces.  As a result, the 802.1q encapsulation will be used. Descriptions are put on the trunk ports indicating what peer switch they are uplinked to.  This is done to provide more at a glance information when looking at the configuration. The commands to configure the trunks in ABC Law Firm’s network are indicated below for each respective switch.

Core Switch

Interface 10gige 1/1

Description Uplink to Access Switch 1

Switchport mode trunk

Switchport nonnegotiate

switchport trunk encap dot1q

switchport trunk allowed vlan all

No shut

Interface 10gige 1/2

Description Uplink to Access Switch 2

Switchport mode trunk

Switchport nonnegotiate

Switchport trunk encap dot1q

Switchport trunk allowed vlan 3, 10

No shut

Interface 10gige 3/1

Description Uplink to Access Switch 1

Switchport mode trunk

Switchport nonnegotiate

Switchport trunk encap dot1q

Switchport trunk allowed vlan all

No shut

Access Switch 1

Interface 10gige 1/1

Description Uplink to Core Switch

Switchport mode trunk

Switchport nonnegotiate

Switchport trunk encap dot1q

Switchport trunk allowed vlan all

No shut

Interface 10gige 3/1

Description Uplink to Core Switch

Switchport mode trunk

Switchport nonnegotiate

Switchport trunk encap dot1q

Switchport trunk allowed vlan all

No shut

Interface 10gige 3/2

Description Uplink to Access Switch 2

Switchport mode trunk

Switchport nonnegotiate

Switchport trunk encap dot1q

Switchport trunk allowed vlan 3, 10

No shut

Access Switch 2

Interface 10gige 1/1

Description Uplink to Core Switch

Switchport mode trunk

Switchport nonnegotiate

Switchport trunk encap dot1q

Switchport trunk allowed vlan 3, 10

No shut

Interface 10gige 3/1

Description Uplink to Access Switch 2

Switchport mode trunk

Switchport nonnegotiate

Switchport trunk encap dot1q

Switchport trunk allowed vlan 3, 10

No shut

  - Spanning tree configuration

The spanning tree protocol allows the use of redundant links on layer 2.  The spanning tree protocol must first elect a root switch.  A network can be left alone to elect its own root bridge but it may not choose the most advantageous one for the network.  It is advisable to force the switch the engineer chooses to become the root switch.  This is done by increasing the priority of the switch which is done by lowering the priority setting value or by using the key word “root primary” and “root secondary”.  A root switch is elected for each vlan that is configured on the switch.  Therefore, if the engineer is designating a specific switch as a root switch it should probably be configured for each vlan on that switch.  The Core switch was designated as the root switch for each Vlan.

In spanning tree, when multiple ports exist to the same destination, traffic will only be forwarded out one of the ports. In addition to a root switch being able to be forced via setting the switch priority, the forwarding port can also be designated by lowering its port cost.  For our network, we want the core switch to be the root for all Vlans and all traffic destined for the Core switch should be prioritized out the port that is directly connected to the Core switch. The initial spanning tree configuration is indicated below for each of the respective switches.

Core Switch

Spanning-tree vlan 1 root primary

Spanning-tree vlan 2 root primary

Spanning-tree vlan 3 root primary

Spanning-tree vlan 10 root primary

Spanning-tree vlan 20 root primary

Interface 10gige 1/1

Spanning-tree cost 1

Interface 10gige 1/2

Spanning-tree cost 1

Access Switch 1

Spanning-tree vlan 1 root secondary

Spanning-tree vlan 2 root secondary

Spanning-tree vlan 3 root secondary

Spanning-tree vlan 10 root secondary

Spanning-tree vlan 20 root secondary

Interface 10gige 1/1

Spanning-tree cost 1

Access Switch 2

Interface 10gige 1/1

Spanning-tree cost 1

# Appendices (Artifacts)

The following documents are within the Artifacts folder, which accompanies this document.

Manufacturer Data Sheets

Cisco Aironet 1130AG Series Access Point Datasheet

Cisco WS-C6500E Catalyst Series Datasheet

Cisco WS-G5484 Ethernet Interface Module Datasheet

Panduit Armored Fiber Cable

Panduit CN1 Net-Access Cabinet

Trip Lite N490016CSC Fiber Patch Panel

Cisco ASA 5500

Misc. Documents

Team-A Business Practitioner

Team-A Professor Feedback 2009-feb-05

Vision and Scope Document 2009-feb-22 REVISION

Network Diagrams

Existing Network

Network Diagram Existing

Network Switch Connectivity Existing

Rack Datacenter Existing

Reconfigured Network

Access Switch 1 Port Details

Access Switch 2 Port Details

Building A Floor 1

Building A Floor 2

Building B

Café Wireless Access Diagram

Core Switch Port Details

Network Diagram Reconfiguration

Network IP Schema

Network Switch Connectivity Reconfiguration

Racks Datacenter Network Future

Project Plan

Project Master Gantt Chart

Project Milestones Gantt Chart

Team Meeting Minutes

Team Meeting Minutes 2009-jan-17

Team Meeting Minutes 2009-feb-14

Mar 1 Group Conversation Final Product

Feb 20 Charles David

Feb 22 Group Deliverables Conversation